## Action Plan
PROPERTIES & BURIAL GROUNDS FIVE YEAR ACTION PLAN 2023 - 2028
Project Name | Priority & Timeframe | Finance options/constraints | Partners | Lead Cllr. for delivery | Ongoing maintenace and costs
Cemeteries & Churchyard tree safety audit | High - completion Sept 2023 | From current budget and earmarked funds estimated circa £350 | TWBC for permission to work on trees in a conservation area | Cllr. Gilbert | Dependant on results of safety audit
Identifying Land for Woodland Burials | Low - when land becomes available | £3,800 in EMF |  | Cllr. Gilbert | Dependant on land acquired
Vestry Hall heating | High - as soon as suitable heating method identified | £500 in EMF |  | Cllr. Gilbert | Dependant on heat source used
Vestry Hall interior decoration | Mid - 2024-2025 | £10,700 in EMF |  | Cllr. Gilbert | Nil
Tower Room Refurbishment | High - 2023-2024 | £5000 in EMF |  | Cllr. Gilbert | Nil
Vestry Hall Cottage refurbishment | Low - when current tenants vacate | £20,500 in EMF |  | Cllr. Gilbert | Nil
Parish Office Refurbishment | Low - 2026-2028 | £1,680 In EMF |  | Cllr. Gilbert | Nil
Vestry Hall - Secondary glazing | High - 2023 | Quotes being sought UKSPF Grant/General cash fund | TWBC Conservation Architect | Cllr. Gilbert | Ordered
Council Chamber - replacement chairs | High 2023-2024 | Current budget |  | Cllr. Gilbert | Nil
Vestry Hall replacement curtains | High 2023 | UKSPF Grant |  | Cllr. Gilbert & Fletcher | Completed - April 2023
Vestry Hall Kitchen refurbishment/upgrade | Mid - 2024-2026 | Project requires budget allocation | TWBC Conservation Architect | Cllr. Gilbert | Nil
Bus Shelter Provision | Mid - 2024-2026 | Subject to grant Availability | KCC | Any Committee Member | Nil

## St. Dunstan's
Notes: St. Dunstan's Churchyard
1. Contract for grounds maintenance taken over by Policy & Resources April 2004 | 22. Dead wooding of lime trees (Carriers Rd side only) Autumn 2015
2. Paths that are the responsibility of the Parish Council were re-laid in 1998. | 23. Signs erected for 'dogs on a lead' Autumn 2015
3. Post & rail fencing along Jockey Lane car park - 1997. | 24. Two new benches sited in memory of M. Camburn & Dr. Hooper - 2016
4. Part of lower wall repaired in 1997. | 25. Tree report by Discover Trees - Sept 2016
5. Trees Inspected in 1998 | 26. Tree surgery undertaken Feb & Oct 2017
6. Lime Trees dead wooded in Spring 2003, 2007(due again 2011/2012)*put on hold spring 2007 to consider major works
7. Turkey Oak removed in Spring 2003 | 27. Magnolia tree pruned professionally June 2017
8. Post & rail fence along Jocky Lane Car Park (top section) replaced August 2004 | 28. Application to install safety handrail submitted Sept 2018, installed Feb 2019
9. Repointing of Church yard wall/Carriers Road side - to be considered in 2004/5 budget (agreed not yet necessary)
10.Garden of Remembrance commenced 2004/Records kept by St. Dunstans Church Office
11.Wall top right by School repaired Summer 2005/top middle Summer 2006 | 29. Area planted to wilding Oct 2019
12. Bench installed Autumn 2005 (replacement) - top right of main path. | 30. Visual tree safety survey completed Sept 2020
13. Bench installed top right of side path towards Ball Field in memory of Dennis Banks - October 2007
14. One lime tree felled and the rest reduced by 30% overall - January 2008 - Stumps ground out 2009 | 31. Repointing repairs to wall undertaken August 2021
15. Churchyard wall repointed on first three bays September 2009
16. Bund removed near to Church Gates - October 2009
17. Overhanging branches of Lime Tree adj Church Gates lopped 2011
18. New fence alongside Jockey Lane Car Park - Summer 2012
19. New bench near west door - in memory of John Soar - Spring 2012
20. Relocation of Turkey Oak stone to the Jockey Lane car park 2014
21. Reshaping of Yew Tree Summer 2015
22. Dead wooding of lime trees (Carriers Rd side only) Autumn 2015
23. Signs erected for 'dogs on a lead' Autumn 2015
24. Two new benches sited in memory of M. Camburn & Dr. Hooper - 2016
25. Tree report by Discover Trees - Sept 2016
26. Tree surgery undertaken Feb & Oct 2017
27. Magnolia tree pruned professionally June 2017
28. Application to install safety handrail submitted Sept 2018, installed Feb 2019
29. Area planted to wilding Oct 2019
30. Visual tree safety survey completed Sept 2020
31. Repointing repairs to wall undertaken August 2021
32. Visual tree safety survey undertaken Oct 2023

## Golford Cemetery
Notes: Golford Cemetery
1. Grounds contract taken over by Policy & Resources April 2004
2. Chapel refurbished 1996 / Cracks have been monitored since
3. Some paths were re-laid in 1995
4. Chairs in chapel donated by Congregational Church in 1994
5. 50 Hymn Books donated by K.B. Sills in 1996
6. Ditches cleared 2000
7. 4 Cypress trees removed - 2001/2002
8. Gates and posts refurbished and gate rehung 2002
9. New gate and hard surface entrance in Coursehorn Lane
gate transferred from Siss and rehung with new posts - 2003
10.Additional Land (Woodland Burials) - Future item
11. Repairs to Bell Tower 2003
12. Clearance of bund Spring 2003/Summer 2006
13. Wiring in of Yews - programmed for 2003 (not done following advice)
14. Deed of Easement - Dulwich College Prep School - sight lines
- north east boundary - 2003 - Works carried out Spring 2007
15. Stained Glass Window - Autumn - Installed 2005
16. Centenery Celebrations 2005 - granite set & noticeboard
donated. Flower Festival May 2005
17. Bell - Golford Chapel - cracked?
18. Stained Glass Window - Summer - installed 2005
19. Chapel redecorated Spring 2006
20. Stained Glass Windows - Spring & Winter installed 2006
21. Mortuary converted into disabled toilet - Completed Spring 2007
22. Stained Glass Windows installed Feb, May and June, Sept 2007
23. German Concert Organ donated by Mrs Nora Prior January 2008
24. Dedication Service and Flower Festival May 2008. Visitor Book donated.
25. Name plaques for window sponsors donated by Garry Blanch - 2008
26. Golford Windows leaflets produced Spring 2009
27. Bench donated on north side - Summer 2009
28. Bell Tower re-roofed & bell repaired Spring 2011
29. New Main + side gates October 2011
30. Six chairs purchased from St. Dunstans Church - Spring 2012
31. New noticeboard donated by Perigoes October 2013
32. Container purchased as storage facility - Nov 2014
33. Toilet redecorated and exterior redecoration of the Chapel Summer 2015
34. Oak Fence replaced at entrance - Spring 2015
35. New heating system installed in Chapel June 2017
36. Path repairs undertaken August 2017
37. Visual Tree safety survey undertaken Sept 2020
38. Turning circle railings & drop bollards installed October 2021
39. Visual tree safety survey undertaken Oct 2023

## Sissinghurst Cemetery
Notes: Sissinghurst Cemetery
1. Grounds maintenance contract taken over by Policy & Resources April 2004
2. New section of Cemetery laid out in Oct 1996.
3. New Hedge planted 1998
4. Access works completed for school play area 1999
5. Half of centre and north paths repaired in 2000
6. Drainage of central section of cemetery carried out in 2001
7. New gate and posts 2003
8. New bench installed in old part of cemetery - 2003
9. New shed 2003
10. Clearance of bund - Spring 2004/Summer 2006
11. Lych gate erected May 2005 + water butt & guttering added 2006
12. New bench installed at far end of old cemetery Spring 2007
13. Right and left hand side paths relaid Autumn 2006
14. Lower Central path relaid Autumn 2008
15. New bench installed at north side of old part 2009
17. Bun Penny Bench replaced October 2011 with original plaque attached.
18. Two paths relaid - middle and lower right hand side - Spring 2012
19. Bund emptied September 2013
20. Boundary treatment and fencing erected by developers of old school site - 2016
21. Tree safety report commissioned Winter 2016
22. Tree Surgery undertaken Oct 2017
21. Tree Surgery undertaken Nov 2018
22. Visual tree safety survey untaken Sept 2020
23. Visual tree safety survey undertaken Oct 2023

## War Memorials
Notes: Cranbrook and Sissinghurst War Memorial
1. Contract originally funded by Cooper Trust/ incorporated in a contract from April 2002. Contract is continuous as long as both parties are content.
2. War Memorial - Cleaned 2003 Cost £185 - Cleaned annually by Reflections prior to Remembrance Service
3. Some repointing carried out Summer 2005
4. Howitzer Gun is restored by Army Cadets and REME and reinstated at Memorial in July 2008 with a parade and service.
5. Hop Plough donated by Brattle Farm Museum - November 2008
6. Howitzer repainted 2011 & Wooden strips for hanging wreaths renewed 2011
7. Cranbrook War Memorial wall damaged in an RTC September 2015, repair completed prior to Remembrance Parade
8. Howitzer rust treated and painted October 2017
9. Contact for grounds maintenance awarded to A.F Garden Services Apr 18
10. Hedge on boundary heavily pruned Dec 2020 and February 2023

## Vestry Hall
Notes: Vestry Hall
1.Vestry Hall Roof - Remedial repairs carried out in 2001
2.Remedial work carried out to chimney over Council Chamber and on front of Vestry Hall 2001
3.Floor, sanded, relaquered and repaired August 2001
4.Audio Loop installed 2004
5.Disabled Toilet and Threshold installed 2004
6.New lighting with dimmer switches installed 2004
7.External Painting carried out 2004
8.Balcony stairs redecorated/emergency lighting installed 2004
9.Gents toilet and kitchen painted in 2004
10.Lead roof renewed January 2005
11. Ladies toilets painted December 2005
12. Stairwell and Landing painted & balcony carpeted December 2005
13.Old Fire Station converted to Information Centre and Parish Officer 2005 (formally opened by HRH Princess Royal 9th December 2005)
14.Tower Room roof releaded Summer 2006
15. Small lead roof renewed 2006
Stairlift to Hall & Chamber - not considered suitable by Stenna 2007 | 31.Interior Entrance redecoration completed August 2019
16. New kitchen - listed building consent/B. Regs obtained Autumn 2008 - New Kitchen went in August-September 2009
17. Interior Painting carried out in August - September 2009 + new storage area in old kitchen and other alterations all part of works as above.
18. 120 new chairs purchased September 2009 -old chairs scrapped
19. Floor sanded by Bishops September 2009
20. Windows stripped by specialist and sanded down
to a natural finish - May - October 2009
21. Bow window on front releaded - Sept 2010
22. Floor treated by Bishops - December 2010
23. New wooden floor - July/August 2012
24. New hob for cooker - Autumn 2012
25. New starter switches for all lights in Hall & Chamber
26. LBC applied for to replace side doors Sept 2017 completed Feb 18
27. Interior decoration of entrances scheduled for Nov 2017
28. Fire Risk Assessment carried out May 2018
29. Exterior decoration completed April 2019
30. Repairs to roof April 2019. Windows cleaned inside and out.
31.Interior Entrance redecoration completed August 2019
32. Session rate increase by £2 per hour from April 2020
33. Hearing loop replaced July 2020
New thermal curtains hung April 2023

## Parish Office
Notes: Parish office
Converted from Caretakers Garage and Boiler Room - Completed May 2005
Lease with TWBC July 2006 - Ongoing
LBC applied for installation of 24/7 Defib installed in entrance Sept 2017
Defib installed Jan 2018
New boiler filtted April 2021
Redecorated - Autumn 2012
Repairs to flat roof completed Summer 2016
TWBC surrendered lease 25th March 2020
Security alarm fitted in Vestry Hall & Info Centre Aug 2021

## VH Cottage
Notes: Vestry Hall Cottage
Caretakers are responsible for internal decoration of cottage
External Painting carried out 2004
Doors painted with fire retardent coating Dec 2019
Replacement fire alarms supplied & fitted by KFRS Sep 2016
Survey on condition of cottage - Dec 2015
Replacement of bathroom floor, bedroom ceiling, damp repairs 2017
New boiler fitted and hot water tank fitted June 2021

## Angley Cottage
Notes: Angley Cottage
New Gate 2003
Re Roofed 2005
Externally Painted 2004
Heat ventilation system - winter 2012
Vacated by Tenant - August 2009 - not fit for human habitation
Refurbished -2010/2011
New Tenant April 2011
Repairs to roof ridge tiles and front door + canopy Nov 2019
Electrical inspection undertaken in Nov 2019

## BS, TB, PF, N, B
Notes: Bus shelters/Telephone boxes/Penny Farthing/ Noticeboards/Benches
Bus Shelters owned by the Parish Council are:-
Wilsley Pound - Jubilee Field,Sissinghurst, Hartley Court Gardens and Swifts View, Common Road - last cleaned Sept 2018
Bus Shelter - Hartley - demolished in a traffic accident - replaced July 2007 - cost borne by car drivers insurance
New Bus Shelter at Woodland - Spring 2014
See entire list of benches - filed in Asset Register | Schedule of repair and maintenance of benches commenced Summer 2019
New bench - Common Road / Cleavers bus stop 2012 | Repairs to Millenium board September 2021
New bench - nr bus stop Greenways, Cranbrook - Winter 2012 | Refurbishment to Penny farthing Oct 2022
New Bus Shelter at Common Road/Cleavers - Summer 2015
Noticeboard on the exterior wall of Vestry Hall repaired - Autumn 2015.
Benches and noticeboards in Cranbrook varnished by Cranbrook in Bloom Summer 2015
New bench in memory of Philip Marley March 2016
Sissinghurst Village sign refurbished - Summer 2016
2 BT red boxes adopted 2016 @ Bakers Cross and Swifts View
Schedule of repair and maintenance of benches commenced Summer 2019
Repairs to Millenium board September 2021
Refurbishment to Penny farthing Oct 2022